## PM_General Responsibilites
Project Management Responsibilities
Tasks | Contractor Name | Franklin Southampton | Notes
Designate Contractor project manager, system engineer, site manager, training manager, field service manager and provide contact information within fifteen (15) days of contract award
Approve Contractor project manager
Direct the project team’s personnel and subcontractors and assist in resolving project issues
Establish project communications protocol and maintain transmittal log
Establish and maintain a master project schedule for the design, implementation and acceptance of the system.
Provide schedule updates to the CLIENT with each monthly status report, or more frequently as needed, to address changing circumstances.
Conduct monthly on-site project review meetings, or more often as needed, to address specific issues.
Conduct monthly project teleconferences, including, as needed, Web-based meeting spaces, between scheduled project review meetings, or more often as needed to address specific issues.
Develop and maintain risk/issue assessment, tracking, resolution, escalation and closeout
Develop change orders and present to Client for written approval prior to work commencing
Review and approve/deny change order, in writing (within 10 days of receipt)
Submit invoices based upon contract payment schedule with all supporting detailed information to include current project status report and current project schedule.
Review and approve or submit deficiencies for invoices within 10 days of receipt.
General Project Responsibilities
Tasks | Contractor Name | Franklin Southampton | Notes
Notify the CLIENT of Contractor's intent to procure subcontractor(s) to perform tasks and/or provide equipment on the project.
Provide a list of proposed subcontractor(s), the tasks that they will perform and/or equipment that they will provide, and project references
Mutually agree on qualifications of proposed subcontractors and key personnel.
Provide the CLIENT information on its subcontractors’ personnel for the sake of criminal background checks and the issuance of temporary identification cards.
Schedule and provide site knowledgeable person to answer Contractor site questions on site surveys
Conduct site survey(s) and provide recommendations
Perform tower mapping and structural analyses
Develop required drawings
Develop network plans and IP backhaul requirements
Develop tower antenna placement plans
Develop frequency plans
Develop coverage maps
Develop site electrical loads
Develop preliminary cutover plan
Develop formal project schedule
Prepare acceptance test procedure (ATP) documents
Prepare one set of FCC license applications for Client’s submission & pay 1st time coordination fees
Sign and submit FCC license applications
If required, prepare additional FCC license applications and pay coordination fees
Acquire property for any new customer-owned greenfield sites (if required)
Furnish one set of technical documents to support site lease efforts
Arrange for site lease for any non-customer-owned sites (if required)
Perform RF antenna sweep on existing transmission lines and antennas that will be reused
Project Kickoff Meeting
Tasks | Contractor Name | Franklin Southampton | Notes
Conduct the Project Kickoff Meeting at a location provided by the Client with the Client project team members within fifteen (15) days after contract signing or other customer notification to proceed
Assemble project team and travel to the Client location
Assemble Client project team for Kickoff Meeting
Present preliminary information on sites and system design
Provide information on status of sites, frequencies, etc.

## DDR
Detailed Design Review (DDR) Deliverables
Tasks | Contractor Name | Frankin Southampton | Notes
Detailed Project schedule
System Configuration - block diagrams
List of deliverable equipment for each site
List of System Operations – Features & Functions
Network connection plan and backhaul requirements
Tower antenna placement drawings
Tower Structural Analysis Reports
Antenna system drawings
Coverage prediction maps
Frequency plans
Combiner plans
Site plot drawings
Shelter floor plan drawings
Rack elevation drawings
AC power and BTU requirements
Plan for Fleet Mapping
Submit Draft Acceptance Test Plans: 1. Microwave/Connectivity Network 2. Radio System 3. BER and Signal Strength (for information only) 4. DAQ Voice Quality Coverage Acceptance (identified service areas) 5. 30-day Operational
Draft cutover plan, include fall back plan
Identify FCC licensed frequencies that meet contour limits and fulfill the frequency plan, in accordance with the project schedule
Acquire FCC approved frequency licenses
Detailed Design Review (DDR)
Tasks | Contractor Name | Frankin Southampton | Notes
Provide all DDR deliverables for review (15 days prior to DDR)
DDR Review Meeting
Review DDR documents
Conduct the DDR no more than 120 days after contract execution
Provide comments from the design following DDR meeting (within 10 days)
Revise DDR documents (within 15 days)
Approve DDR documents (within 10 days)

## General Site Responsibilities
General Site Responsibilities
Tasks | Contractor Name | Frankin Southampton | Notes
Coordinate with federal, state, and local government agencies, as required
Provide access to necessary buildings and sites, including temporary ID badges for Contractor, if needed.
Provide parking permits for Contractor project team for any restricted parking areas
Provide adequate road access for delivery vehicles
Provide temporary parking to off-load equipment at all buildings and sites
Clean up site and remove all installation debris
Remove any hazardous material found on site (to the extent the hazardous material is not generated by Vendor/Contractor)
If required, coordinate with the utility company to provide appropriate utility transformer additions or upgrades required to provide the adequate AC power needed for each site
Provide reasonable remediation for adequate AC utility connection
Comply with FCC OET65 Signage requirements(https://www.fcc.gov/general/oet-bulletins-line) for any new tower construction.
Develop sites and install materials in accordance with industry and Vendor standards
Procure CAD vendor services to upgrade the existing CAD system to be compatible with the GPS location data, if the GPS services option is exercised

## Site 1
Site 1 - (Insert Site Name)
Site Tasks | Contractor Name | Frankin Southampton | Notes
Complete one set of forms/applications to support zoning permits and approval for site changes
Sign and submit forms/applications to support zoning permits and approvals for site changes.
Perform physical path surveys for each microwave path (microwave path studies are not final until a physical survey is made)
Provide existing site plans (if available)
Conduct grounding inspection and provide recommendations
Conduct site survey(s) and provide recommendations
Tower Tasks | Contractor Name | Frankin Southampton | Notes
Stake out the desired location for tower (if new tower)
Grade land, construct silt fences, and remove weeds and brush
After assurances have been made that this site can be developed, develop site plot drawings of compound showing new tower, shelter, generator, and fuel tank locations
Perform geotechnical investigation for tower leg foundations in accordance with TIA-222 standards for new towers, and review results with at DDR
If geotechnical investigation results indicate a foundation design is required to address other than typical soil conditions. Submit a site-specific foundation design, and pricing change request, at, or prior too, DDR
Prepare new tower NEPA/SHPO environmental studies and THPO filings
Prepare and submit construction permits for new tower
Prepare and submit electrical permits
Identify specific tower attachment points to mount new antennas per the system design
Confirm availability of tower attachment points for proposed antennas
Perform tower mapping and structural analysis on existing tower and provide results at DDR. If tower fails load analysis, Contractor will provide quotes to strengthen tower (if possible), replace the tower, or provide site acquisition services.
Strengthen or replace tower (if required by structural analysis results) at an agreed upon additional cost and schedule adjustment
Provide space on existing tower to mount new system antennas at Contractor specified locations as part of the site lease(s)
Provide adequate space on cable ice bridge, and tower cable ladders, to support new cable runs
Install new antenna(s) using appropriate side arms and mounting hardware
Install antenna coax, connectors and jumpers, using cable clamps to properly secure cable to tower, and add grounding kits at the top, bottom, and on ice bridge
Install new tower top amplifiers for the P25 radio system
Install antenna lightning protection devices on each transmission line LMR run after it enters shelter via cable entry port; ground device to main ground bus bars
If required, install new microwave dish(es), on pipe mounts with anti-sway kits
Install ice shields over microwave dishes if not at the top of tower
Install new microwave waveguide or coaxial feed lines, secure to cable ladder(s), and add grounding kits at the top, bottom, and on ice bridge
Tag and identify each new antenna line
Sweep test each new antenna line in accordance with Contractor's “Transmission Line Analysis (Antenna Sweep) procedure
Shelter Tasks | Contractor Name | Frankin Southampton | Notes
Provide and install new shelter
Grade land, construct silt fences, and remove weeds and brush
Provide floor space in existing RF shelter for new equipment racks and DC battery plant or UPS used in the new design
Provide adequate shelter/equipment room utility AC electrical power, single-point ground system, and HVAC
Provide new cable entry port(s) if required
Upgrade existing interior ground system
Provide additional cable ladder for new equipment row
If needed, prepare and submit electrical permits on behalf of the customer
Install new DC power plant or UPS and wire to racks
Provide demarcation blocks for connection to existing legacy radios to be used in interoperability system
Connect site alarms to alarm punchblock (i.e smoke detector, generator, ATS, Temperature, etc.)
Generator Tasks | Contractor Name | Client Name | Notes
Stake out the desired location for new generator pad (and fuel tank pad if necessary)
Have an architectural firm develop site compound plot drawings of compound showing tower, shelter, new generator (and fuel tank if necessary)
Complete one set of forms/applications to support zoning permits and approvals
Sign and submit forms/applications to support zoning permits and approvals for site changes.
Prepare and submit construction permits for new generator (and fuel tank if necessary)
Prepare and submit electrical permits
Grade land, construct silt fences, and remove weeds and brush
Construct/pour generator pads (and fuel tank pad if necessary)
Transport, off-load, and set new generator on pad (and fuel tank if necessary)
Install ATS
Trench in generator electrical service and control circuits to shelter-mounted ATS
Ground generator (and fuel tank if necessary) to tower/shelter ground system
Fill generator fuel tank (first fill)
Provide factory generator technician for first-start service

## Site 2
Site 2 - (Insert Site Name)
Site Tasks | Contractor Name | Frankin Southampton | Notes
Complete one set of forms/applications to support zoning permits and approval for site changes
Sign and submit forms/applications to support zoning permits and approvals for site changes.
Perform physical path surveys for each microwave path (microwave path studies are not final until a physical survey is made)
Provide existing site plans (if available)
Conduct grounding inspection and provide recommendations
Conduct site survey(s) and provide recommendations
Tower Tasks | Contractor Name | Frankin Southampton | Notes
Stake out the desired location for tower (if new tower)
Grade land, construct silt fences, and remove weeds and brush
After assurances have been made that this site can be developed, develop site plot drawings of compound showing new tower, shelter, generator, and fuel tank locations
Perform geotechnical investigation for tower leg foundations in accordance with TIA-222 standards for new towers, and review results with at DDR
If geotechnical investigation results indicate a foundation design is required to address other than typical soil conditions. Submit a site-specific foundation design, and pricing change request, at, or prior too, DDR
Prepare new tower NEPA/SHPO environmental studies and THPO filings
Prepare and submit construction permits for new tower
Prepare and submit electrical permits
Identify specific tower attachment points to mount new antennas per the system design
Confirm availability of tower attachment points for proposed antennas
Perform tower mapping and structural analysis on existing tower and provide results at DDR. If tower fails load analysis, Contractor will provide quotes to strengthen tower (if possible), replace the tower, or provide site acquisition services.
Strengthen or replace tower (if required by structural analysis results) at an agreed upon additional cost and schedule adjustment
Provide space on existing tower to mount new system antennas at Contractor specified locations as part of the site lease(s)
Provide adequate space on cable ice bridge, and tower cable ladders, to support new cable runs
Install new antenna(s) using appropriate side arms and mounting hardware
Install antenna coax, connectors and jumpers, using cable clamps to properly secure cable to tower, and add grounding kits at the top, bottom, and on ice bridge
Install new tower top amplifiers for the P25 radio system
Install antenna lightning protection devices on each transmission line LMR run after it enters shelter via cable entry port; ground device to main ground bus bars
If required, install new microwave dish(es), on pipe mounts with anti-sway kits
Install ice shields over microwave dishes if not at the top of tower
Install new microwave waveguide or coaxial feed lines, secure to cable ladder(s), and add grounding kits at the top, bottom, and on ice bridge
Tag and identify each new antenna line
Sweep test each new antenna line in accordance with Contractor's “Transmission Line Analysis (Antenna Sweep) procedure
Shelter Tasks | Contractor Name | Frankin Southampton | Notes
Provide and install new shelter
Grade land, construct silt fences, and remove weeds and brush
Provide floor space in existing RF shelter for new equipment racks and DC battery plant or UPS used in the new design
Provide adequate shelter/equipment room utility AC electrical power, single-point ground system, and HVAC
Provide new cable entry port(s) if required
Upgrade existing interior ground system
Provide additional cable ladder for new equipment row
If needed, prepare and submit electrical permits on behalf of the customer
Install new DC power plant or UPS and wire to racks
Provide demarcation blocks for connection to existing legacy radios to be used in interoperability system
Connect site alarms to alarm punchblock (i.e smoke detector, generator, ATS, Temperature, etc.)
Generator Tasks | Contractor Name | Frankin Southampton | Notes
Stake out the desired location for new generator pad (and fuel tank pad if necessary)
Have an architectural firm develop site compound plot drawings of compound showing tower, shelter, new generator (and fuel tank if necessary)
Complete one set of forms/applications to support zoning permits and approvals
Sign and submit forms/applications to support zoning permits and approvals for site changes.
Prepare and submit construction permits for new generator (and fuel tank if necessary)
Prepare and submit electrical permits
Grade land, construct silt fences, and remove weeds and brush
Construct/pour generator pads (and fuel tank pad if necessary)
Transport, off-load, and set new generator on pad (and fuel tank if necessary)
Install ATS
Trench in generator electrical service and control circuits to shelter-mounted ATS
Ground generator (and fuel tank if necessary) to tower/shelter ground system
Fill generator fuel tank (first fill)
Provide factory generator technician for first-start service

## Site 3
Site 3 - (Insert Site Name)
Site Tasks | Contractor Name | Frankin Southampton | Notes
Complete one set of forms/applications to support zoning permits and approval for site changes
Sign and submit forms/applications to support zoning permits and approvals for site changes.
Perform physical path surveys for each microwave path (microwave path studies are not final until a physical survey is made)
Provide existing site plans (if available)
Conduct grounding inspection and provide recommendations
Conduct site survey(s) and provide recommendations
Tower Tasks | Contractor Name | Frankin Southampton | Notes
Stake out the desired location for tower (if new tower)
Grade land, construct silt fences, and remove weeds and brush
After assurances have been made that this site can be developed, develop site plot drawings of compound showing new tower, shelter, generator, and fuel tank locations
Perform geotechnical investigation for tower leg foundations in accordance with TIA-222 standards for new towers, and review results with at DDR
If geotechnical investigation results indicate a foundation design is required to address other than typical soil conditions. Submit a site-specific foundation design, and pricing change request, at, or prior too, DDR
Prepare new tower NEPA/SHPO environmental studies and THPO filings
Prepare and submit construction permits for new tower
Prepare and submit electrical permits
Identify specific tower attachment points to mount new antennas per the system design
Confirm availability of tower attachment points for proposed antennas
Perform tower mapping and structural analysis on existing tower and provide results at DDR. If tower fails load analysis, Contractor will provide quotes to strengthen tower (if possible), replace the tower, or provide site acquisition services.
Strengthen or replace tower (if required by structural analysis results) at an agreed upon additional cost and schedule adjustment
Provide space on existing tower to mount new system antennas at Contractor specified locations as part of the site lease(s)
Provide adequate space on cable ice bridge, and tower cable ladders, to support new cable runs
Install new antenna(s) using appropriate side arms and mounting hardware
Install antenna coax, connectors and jumpers, using cable clamps to properly secure cable to tower, and add grounding kits at the top, bottom, and on ice bridge
Install new tower top amplifiers for the P25 radio system
Install antenna lightning protection devices on each transmission line LMR run after it enters shelter via cable entry port; ground device to main ground bus bars
If required, install new microwave dish(es), on pipe mounts with anti-sway kits
Install ice shields over microwave dishes if not at the top of tower
Install new microwave waveguide or coaxial feed lines, secure to cable ladder(s), and add grounding kits at the top, bottom, and on ice bridge
Tag and identify each new antenna line
Sweep test each new antenna line in accordance with Contractor's “Transmission Line Analysis (Antenna Sweep) procedure
Shelter Tasks | Contractor Name | Frankin Southampton | Notes
Provide and install new shelter
Grade land, construct silt fences, and remove weeds and brush
Provide floor space in existing RF shelter for new equipment racks and DC battery plant or UPS used in the new design
Provide adequate shelter/equipment room utility AC electrical power, single-point ground system, and HVAC
Provide new cable entry port(s) if required
Upgrade existing interior ground system
Provide additional cable ladder for new equipment row
If needed, prepare and submit electrical permits on behalf of the customer
Install new DC power plant or UPS and wire to racks
Provide demarcation blocks for connection to existing legacy radios to be used in interoperability system
Connect site alarms to alarm punchblock (i.e smoke detector, generator, ATS, Temperature, etc.)
Generator Tasks | Contractor Name | Frankin Southampton | Notes
Stake out the desired location for new generator pad (and fuel tank pad if necessary)
Have an architectural firm develop site compound plot drawings of compound showing tower, shelter, new generator (and fuel tank if necessary)
Complete one set of forms/applications to support zoning permits and approvals
Sign and submit forms/applications to support zoning permits and approvals for site changes.
Prepare and submit construction permits for new generator (and fuel tank if necessary)
Prepare and submit electrical permits
Grade land, construct silt fences, and remove weeds and brush
Construct/pour generator pads (and fuel tank pad if necessary)
Transport, off-load, and set new generator on pad (and fuel tank if necessary)
Install ATS
Trench in generator electrical service and control circuits to shelter-mounted ATS
Ground generator (and fuel tank if necessary) to tower/shelter ground system
Fill generator fuel tank (first fill)
Provide factory generator technician for first-start service

## System Integration & Staging
Radio System Integration and Staging
Tasks | Contractor Name | Frankin Southampton | Notes
Draft Radio Staging Acceptance Test Plans as part of the DDR package
Approve Radio Staging Acceptance Test Plans (30 days prior to test)
Insert equipment delivery dates into the material planning system
Place equipment orders upon DDR approval
Manufacture all infrastructure equipment
Assemble equipment in Radio staging area(s) on a per site basis (tests may occur at different times and at different physical locations)
Perform Radio Staging configuration and pre-test
Provide appropriate personnel to participate in/witness the Radio staging acceptance tests
Perform the Radio staging acceptance tests
Provide Radio stage acceptance tests results (within 10 of each test completion)
Review and approve the Radio staging test results (within 10 days of completion of each test)
Provide written approval of all equipment shipments as part of staging test approval
Microwave System Integration and Staging
Tasks | Contractor Name | Frankin Southampton | Notes
Draft Microwave Staging Acceptance Test Plans as part of the DDR package
Approve Microwave Staging Acceptance Test Plans (30 days prior to test)
Insert equipment delivery dates into the material planning system
Place equipment orders upon DDR approval
Manufacture all infrastructure equipment
Assemble equipment in Microwave staging area(s) on a per site basis (tests may occur at different times and at different physical locations)
Provide appropriate personnel to participate in/witness the Microwave staging acceptance tests
Perform Microwave Staging configuration and pre-test
Perform the Microwave staging acceptance tests
Provide Microwave stage acceptance tests results (within 10 days of each test completion)
Review and approve the Microwave staging test results (within 10 days of completion of each test)
Provide written approval of all equipment shipments as part of staging test approval

## Shipping and Inventory
Infrastructure Shipping and Inventory
Tasks | Contractor Name | Frankin Southampton | Notes
Break down equipment and ship to sites or secure storage facility
Provide and pay for secure temporary storage facility
Provide detailed Inventory for all shipped equipment
Confirm detailed inventory for all delivered equipment at storage facility
Sort equipment in preparation for site delivery and installation

## System Infrastructure Install
System Infrastructure Installation
System Infrastructure Installation Tasks | Contractor Name | Frankin Southampton | Notes
Deliver equipment to each site
Install equipment, connect to ground system and apply power
Connect all RF cables
Connect all P25 system alarms
Interface to network, verify network connectivity
Dispatch Center Installation Tasks | Contractor Name | Frankin Southampton | Notes
Deliver equipment to each site
Install Consoles and Ground all Equipment
Install Routers
Install Cabling
Install Control Stations and Grounding
Install Control Stations Antennas and Grounding
Install/Configure Radio Gateways
Install Network Management Terminal(s)
Perform Initial Tests
Upgrade/Install New Logging Recorder
Connect Logging Recorder to Radio System, Phone Lines, etc.
Train on new Logging Recorder

## Connect Network Install
Connectivty Network Infrastructure Installation
System Infrastructure Installation Tasks | Contractor | Frankin Southampton | Notes
Deliver equipment to each site
Install equipment, connect to ground system and apply power
Install MW Antennas and connect to ground system
Install Ice Shields over MW antennas
Install/configure microwave dehydrator
Install/configure Fiber interface equipment
Connect waveguide
Interface to radio system, verify network connectivity
Connect all alarm to Connectivity Network NMS
Integrate to Radio System NMS
Install Routers
Install Cabling
Perform Initial Tests

## System Optimization
System Optimization
Tasks | Contractor Name | Frankin Southampton | Notes
Prepare all installed sites for site inspections
Verify microwave/backhaul system is functional and meets reliability specifications
Provide frequencies to use for optimization and testing for the paging system
Verify P25 system levels and parameters are set
Verify P25 system alarm and network management system are operational
Verify system database is installed and operating correctly
Verify proper console configuration/operation
Verify proper P25 system functional operation
Verify proper network switching operation
Verify proper interoperability from gateways
Provide system optimization data/report

## Field Acceptance Testing
Field Acceptance Testing
Tasks | Contractor Name | Frankin Southampton | Notes
Provide appropriate team members to participate in all acceptance tests
Inspect each site (tower sites, dispatch centers, equipment rooms. etc), noting discrepancies on a punch list
Submit site inspection punchlist (within 15 days of site inspections)
Remedy or provide resolution plan for site inspection punchlist items (within 15 days of punchlist received)
Approve site inspection punchlist remedies or resolution plans (within 10 days)
Revise Acceptance Test Plans (not less than 40 days prior to beginning of each test): 1. Microwave/Connectivity Network 2. Radio System 3. BER and Signal Strength (for information only) 4. DAQ Voice Quality Coverage Acceptance (identified service areas) 5. 30-day Operational
Approve Acceptance Test Plans (within 10 days of each Test Plan submission): 1. Microwave/Connectivity Network 2. Radio System 3. BER and Signal Strength (for information only) 4. DAQ Voice Quality Coverage Acceptance (identified service areas) 5. 30-day Operational
Perform Field Acceptance Tests (notice must be given 10 days prior to beginning of each test): 1. Microwave/Connectivity Network 2. Radio System 3. BER and Signal Strength (for information only) 4. DAQ Voice Quality Coverage Acceptance (identified service areas) 5. 30-day Operational
Witness/Participate in Acceptance Tests: (notice must be given 30 days prior to beginning of each test): 1. Microwave/Connectivity Network 2. Radio System 3. BER and Signal Strength (for information only) 4. DAQ Voice Quality Coverage Acceptance (identified service areas) 5. 30-day Operational
Submit Acceptance Test results (within 15 days of each test completion): 1. Microwave/Connectivity Network 2. Radio System 3. BER and Signal Strength (for information only) 4. DAQ Voice Quality Coverage Acceptance (identified service areas) 5. 30-day Operational
Approve Acceptance Test results (within 10 days of each report submission): 1. Microwave/Connectivity Network 2. Radio System 3. BER and Signal Strength (for information only) 4. DAQ Voice Quality Coverage Acceptance (identified service areas) 5. 30-day Operational
DAQ Voice Quality Coverage Acceptance Testing Tasks | Contractor Name | Frankin Southampton | Notes
Provide test vehicles, and drivers for DAQ Voice Quality Coverage Acceptance Test (identified service areas)
Provide test radios for DAQ Voice Quality Coverage Acceptance Test (identified service areas)
Install DAQ Voice Quality Test equipment in testing vehicles
Provide & connect attenuators for test radios for DAQ Voice Quality Coverage Acceptance Test (identified service areas)
Perform Pre-test validation of DAQ Voice Quality Test Configuration
Perform DAQ Voice Quality Acceptance Testing
Retry DAQ Voice Quality test for failed test tiles as defined in the mutually agree upon Acceptance Test Plans. Contractor will coordinate with Client representatives to be present during the retest.

## Terminal Equipment
Terminal Equipment
Shipping and Inventory Tasks | Contractor Name | Frankin Southampton | Notes
Order terminal equipment (mobiles/portables/pagers/control stations) after receipt of Client written approval
Survey control station installation locations
Provide detailed Inventory of terminal equipment (mobiles/portables/pagers/control stations, and subscriber accesories)
Deliver terminal equipment (mobiles/portables/pagers/control stations, and subscriber accesories) after receipt of Client written approval
Confirm detailed inventory for delivered terminal equipment (mobiles/portables/pagers/control stations, and subscriber accesories)
Control Station Radio Tasks | Contractor Name | Frankin Southampton | Notes
Provide access to control station installation locations to meet the project schedule timeline
Program and install control stations and control station antennas
Provide pre and post control station installation assessments, presenting installation documentation for customer acceptance for each control station location.
Provide a representative to review control station installation documentation and provide acceptance for each location
Mobile Radio Tasks | Contractor Name | Frankin Southampton | Notes
Provide a central facility for mobile vehicle installation
Provide vehicles for mobile installation to meet the project schedule timeline
Program and install mobile units
Perform pre and post testing of emergency vehicle systems (Sirens, Lights, MDT's, GPS, etc)
Provide pre and post installation vehicle assessments, presenting installation documentation for customer acceptance for each vehicle
Provide a representative to review installation documentation and provide acceptance for each vehicle
Portable Radio and Pager Tasks | Contractor Name | Frankin Southampton | Notes
Program and distribute portable units with accessories
Program and distribute pager units

## Training, Fleetmapping, Cutover
Training, Fleetmapping, and Cutover
Training Tasks | Contractor Name | Frankin Southampton | Notes
Develop training plan and schedule (collaborative effort)
Identify system administrators
Provide system administrator training
Attend system administrator training
Identify system maintenance technicians
Provide radio system maintenance training
Attend radio system maintenance training
Provide connectivity network maintenance training
Attend connectivty network maintenance training
Provide radio user training
Attend radio user training (including Public Safety Telecommunicators)
Identify radio user trainers
Provide radio user train-the-trainer training
Attend radio user train-the-trainer training
Provide console training (including backup control station training)
Attend console training
Identify console trainers
Provide console train-the-trainer training
Attend console train-the-trainer training
Fleetmapping Tasks | Contractor Name | Frankin Southampton | Notes
Provide workshops for talk-group planning
Attend workshop for talk-group planning
Develop user programming profiles (collaborative effort)
Develop console programming profiles (collaborative effort)
Develop and enter system database
Cutover Tasks | Contractor Name | Frankin Southampton | Notes
Define which interoperability channels are desired during cutover
Create interoperability channels for cutover, using proposed gateways
Agree to cutover date, time, and all necessary participants
Revise Draft Cutover Plan (not less than 40 days prior to beginning cutover)
Review & Approve cutover plan (not less than 30 days prior to beginning cutover)
Notify users of system cutover date
Schedule all required subcontractors needed for cutover
Proceed with system cutover according to cutover plan
Submit letter of conditional system acceptance within 5 days following cutover
Approve conditional system acceptance and sign letter within 10 days of completion of a successful cutover

## Final Acceptance
Final Acceptance
Tasks | Contractor Name | Frankin Southampton | Notes
Removal of decommissioned legacy network, console, or site infrastructure equipment
Submit draft as-built documentation package (15 days prior to submission of final acceptance letter)
Review/Comment on draft as-built and maintenance documentation package (within 15 days)
Submit final drawing as-built and maintenance documentation package (within 15 days)
Submit letter of final system acceptance
Provide warranty and maintenance contact information
Meet with CONTRACTOR to outline warranty/maintenance contact procedures
Outline system support and services requirements
Accept final drawings, as-built, and maintenance documentation package (within 15 days)
Sign letter of final system acceptance (within 10 days of receipt of letter)